## RFC--List_NCTS+DDCOM
RFC-List | Row | Filename (SfA) | ID | Deadline for implementation | Comment | In short | N1 | Impact CD/ED | Note
RFC-List.37 | 1 | RFC_NCTS_0190_IAR-UCCNCTS2478-v1.10(SfA-NPM).docx | RFC_NCTS_0190 | Flexible | - - APPROVED by NPMs - - Recommended to be applied before the NTA (P5) is opened to External Domain. | NCTS-P5 (DDNTA-5.15.0-v1.00 Appendix X stypes.xsd file): ‘CommunicationLanguageAtDestination’ based on 'LanguageCodeType' having pattern extended to lower-case letters. | Yes | ED only | No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 2 | RFC_NCTS_0191_IAR-UCCNCTS2270-v1.20(SfA-NPM+IMPL).docx | RFC_NCTS_0191 | Flexible / Optional | - - APPROVED by NPMs - - Optional - Optimisation. | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-v51.8.0): Correction of the wording of B1820 and B1823 to avoid redundancy / overlap during the validation. [optional] | Yes | CD only | No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 3 | RFC_NCTS_0192_IAR-UCCNCTS2963-v1.20(SfA-NPM+IMPL).docx | RFC_NCTS_0192 | Flexible - AT LATEST 01.12.2023 | - - APPROVED by NPMs - - Recommended to get in in place at latest before AES-NCTS-P5 are interfaced. | NCTS-P5 (DDNTA-5.15.0-v100 - CSE-v51.8.0): Correction of C0153 to make the D.G. ‘COMMODITY CODE’ required in case of 'Export Followed by Transit incl. type TIR'. C0153 removed from CC025C. | No | Both | No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 4 | RFC_NCTS_0193_IAR-UCCNCTS2984-v1.10(SfA-NPM).docx | RFC_NCTS_0193 | Big-bang on 06-MAY-2023 [or when the NTA starts exchanging NCTS-P5 messages on the Common Domain (PROD) if starting after that date] | - - APPROVED by NPMs - - The date of 06.05.2023 is not very strict, the potential impact (to be assssed by each NA) of early/delayed deployement before/after that date is limited to (few?) movements with en route event (incident). Similar approach also in AES. | NCTS-P5 (DDNTA-5.15.0-v1.0.0 - CSE-v51.8.0): Correcting the structure of CD003C, CD038C, CD115C and CD165C to get it aligned to CD001C and al. (consistency for placing D.G. ‘TRANSPORT CHARGES’). | Yes | CD only | No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 5 | RFC_NCTS_0194_IAR-UCCNCTS2547-v1.20(SfA-NPM+IMPL).docx | RFC_NCTS_0194 | Before starting with NCTS-P5 operations on the Common Domain. | - - APPROVED by NPMs - - 1. No CD impact for the countries using the ieCA (correction via CTS/CRP). 2. Likely a low impact for the countries not using the ieCA but having their own convertor for the Common Domain messages. Either they re-use the new CTS version, or they adapt and test their own XSLT package. | NCTS-P5 (CTS-5.7.1-v1.00 for DDNTA-5.15.0-v1.00 - CSE-v51.8.0): Resolving the conflict between C589 and B1854 data group for Data Element 'Place of unloading' (when downgrading conversion). | No | ieCA only | EXTRA IMPLEMENTATION DETAILS INCLUDED IN SUPPORTING DOCUMENT OF DDNTA-5.15.1-v1.00-SfA RFC_NCTS_0194_IAR-UCCNCTS2547-v1.10(SfA-NPM).docx replaced by RFC_NCTS_0194_IAR-UCCNCTS2547-v1.20(SfA-NPM+IMPL).docx
RFC-List.37 | 6 | RFC_NCTS_0195_IAR-UCCNCTS2307-v1.10(SfA-NPM).docx | RFC_NCTS_0195 | Flexible / Documentary | - - APPROVED by NPMs - - Cosmetic (Purely documentary) - No impact on operations | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-v51.8.0): Correction of typos in C0352. | No | Documentary | No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 7 | RFC_NCTS_0196_IAR-UCCNCTS2316-v1.20(SfA-NPM+IMPL).docx | RFC_NCTS_0196 | 01-DEC-2023 | - - APPROVED by NPMs - - This RFC proposal has business continuity impact in Common Domain messages. It must be deployed before the end of the Transitional Period. | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-v51.8.0): TRT E1301 replaced by BRT B1030 to disable conditions not only during TP but also after TP for all open movements released for transit during TP. E1301+C0001 (‘CONSIGNEE’), E1301+C0909 (‘Country of dispatch’), E1301+C0502 (‘Reference number UCR’) at HOUSE CONSIGNMENT level. | No | CD only | No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 8 | RFC_NCTS_0197_IAR-UCCNCTS2983-v1.30(SfA-NPM+IMPL2).docx | RFC_NCTS_0197 | Flexible / As soon as possible | - - APPROVED by NPMs - - Recommended to be applied before the NTA (P5) is opened to Common Domain. | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-v51.8.0): CL172, CL173 and CL175 replaced by CL141 in CD003C, CD115C and CD165C for Office of Destination / Transit / Exit for Transit Declared. Correction of guideline G0203 in CD142C and CD143C. Correction of CD059C (CL141 -> CL176). | Yes | CD only | EXTRA IMPLEMENTATION DETAILS INCLUDED IN SUPPORTING DOCUMENT OF DDNTA-5.15.1-v1.00-SfA RFC_NCTS_0197_IAR-UCCNCTS2983-v1.20(SfA-NPM+IMPL).docx replaced by RFC_NCTS_0197_IAR-UCCNCTS2983-v1.30(SfA-NPM+IMPL2).docx
RFC-List.37 | 9 | RFC_NCTS_0198_IAR-UCCNCTS2944-v1.10(SfA-NPM).docx | RFC_NCTS_0198 | As soon as possible (NA-DE) / Before joining Common Domain | - - APPROVED by NPMs - - This RFC proposal has business continuity impact in Common Domain messages. It must be deployed before the NTA starts NCTS-P5 on Common Domain. | NCTS-P5 (DDNTA-5.15.0-v1.00): Correction of C0587 from the Data Group ‘CUSTOMS OFFICE OF EXIT FOR TRANSIT (DECLARED)’ (in CC013C, CC015C, CC017C, CC029C, CD001C, CD003C, CD038C, CD050C, CD115C, CD165C). Addition of a Guideline for CC013C and CC015C to clarify the usage of this Data Group. Removal of C0587 from CD181C. (also applicable to NCTS-P6) | No | Both | No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 10 | RFC_NCTS_0199_IAR-UCCNCTS2609-v1.10(SfA-NPM).docx | RFC_NCTS_0199 | As soon as possible (NA-DE) / Before joining Common Domain | - - APPROVED by NPMs - - This RFC proposal has business continuity impact in Common Domain messages. It must be deployed before the NTA starts NCTS-P5 on Common Domain. | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-v51.8.0): Correction of R0601 and B1922. | Yes | Both | No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 11 | RFC_NCTS_0200_IAR-UCCNCTS3064-v1.10(SfA-NPM).docx | RFC_NCTS_0200 | As soon as possible / Target date for CRP upgrade 15-FEB-2023 (to be confirmed by DG TAXUD/B3) | - - APPROVED by NPMs - - 1. No CD impact for the countries using the ieCA (correction via CTS/CRP). 2. Likely a low impact for the countries not using the ieCA but having their own convertor for the Common Domain messages. Either they re-use the new CTS version, or they adapt and test their own XSLT package. Consistent with RFC_AES_0137. | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-v51.8.0): Correction of CTS-5.7.1, to avoid a possible violation of C135, C140, R876, TR9120 when downgrading some messages CD001C, CD003C, CD012C, CD038C, CD050C or CD115C. | No | ieCA only | No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 12 | RFC_NCTS_0201_IAR-UCCNCTS2637-v1.10(SfA-NPM).docx | RFC_NCTS_0201 | Flexible / As soon as possible | - - APPROVED by NPMs - - Recommended to be applied before the NTA (P5) is opened to External Domain. | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-v51.8.0): Removal of C0450 from CC029C. | Yes | ED only | No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 13 | RFC_NCTS_0202_IAR-UCCNCTS3110-v1.10(SfA-NPM).docx | RFC_NCTS_0202 | Flexible | - - APPROVED by NPMs - - Ideally to be applied before the NTA (P5) is opened to Common Domain. Flexible considering the low impact on Common Domain. Consistent with RFC_AES_0139. | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-v51.8.0): Removal of T1120 from CD906C and CD917C. | Yes | CD only | No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 14 | RFC_NCTS_0203_IAR-UCCNCTS3099-v1.10(SfA-NPM+IMPL).docx | RFC_NCTS_0203 | Flexible | - - APPROVED by NPMs - - To be defined nationally. This correction cannot justify a delay in the start of NCTS-P5 operations, considering the limited cases with limited impact. External Domain only. | NCTS-P5 (DDNTA-5.15.0-v1.0.0 - CSE-v51.8.0): Correction of the multiplicity of D.G. ‘INVALIDITY GUARANTEE REASON’ in CC055C (9x, aligned to CD205C). | Yes | ED only | ! SFA to NPM AFTER CAB AS REQUESTED BY NA-IE No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 15 | RFC_NCTS_0204_AES0138_IAR-UCCNCTS3151-UCCAES1627-v1.10(SfA-NPM+IMPL).docx | RFC_NCTS_0204 | Big-bang on 06-MAY-2023 [or when the NTA starts exchanging NCTS-P5 messages on the Common Domain (PROD) if starting after that date] | - - APPROVED by NPMs - - The date of 06.05.2023 is not very strict, the potential impact (to be assssed by each NA) of early/delayed deployement before/after that date is limited to (few?) cases with combined or multiple risks. Consistent with RFC_AES_0138. | NCTS-P5 (DDNTA-5.15.0-v1.0.0) & AES-P1 (DDNXA 5.15.0-v1.00) based on CSE-v51.8.0: Correction of C0715 to manage combined risk (national and common) for one or more goods items - New guideline added. [Similar for NCTS-P6] | Yes | CD only | ! SFA to NPM AFTER CAB AS REQUESTED BY NA-DE EXTRA IMPLEMENTATION DETAILS INCLUDED IN SUPPORTING DOCUMENT OF DDNTA-5.15.1-v1.00-SfA RFC_NCTS_0204_AES0138_IAR-UCCNCTS3151-UCCAES1627-v1.00(SfA-NPM).docx replaced by RFC_NCTS_0204_AES0138_IAR-UCCNCTS3151-UCCAES1627-v1.10(SfA-NPM+IMPL).docx
RFC-List.37 | 16 | RFC_NCTS_0205_IAR-UCCNCTS2421-v1.00(SfA-NPM).docx | RFC_NCTS_0205 | Documentary | - - APPROVED by NPMs - - NTA must be aligned to Main Document that is correct. Getting Appendix N aligned to it. | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-v51.8.0): Correction of Appendix N to add the (missing) IE114/IE115 from status "Under enquiry procedure". | No | Documentary | ! SFA to NPM AFTER CAB AS REQUESTED BY NA-BE No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 17 | RFC_NCTS_0206_IAR-UCCNCTS2432-v1.00(SfA-NPM).docx | RFC_NCTS_0206 | Documentary | - - APPROVED by NPMs - - Removing obvious typos and adding some clarifications, removing some minor inconsistencies. | NCTS-P5 (DDNTA-5.15.0-v1.00 – Main Document & Appendices): Correction of typos. | No | Documentary | ! SFA to NPM AFTER CAB AS REQUESTED BY NA-BE No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 18 | RFC_NCTS_0207_CSRD2-CL999-v1.00(SfA-NPM+IMPL).docx | RFC_NCTS_0207 | As soon as possible after 15.01.23, at the latest on 30.01.2023 / Before joining Common Domain | - - APPROVED by NPMs - - Likely low impact (the code 'QP - High seas' should not be used frequently by traders for defining the 'Nationality'). | NCTS-P5: correction and improvement of CL999 (DomainMapping) | Yes | Ref Data | ! SFA to NPM AFTER CAB DEFECT using ieCA PROD No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 19 | RFC_NCTS_0208_IAR-UCCNCTS2945-v1.00(SfA-NPM).docx | RFC_NCTS_0208 | Documentary | - - APPROVED by NPMs - - Removing obvious typos and adding some clarifications, removing some minor inconsistencies. | NCTS-P5 (DDNTA-5.15.0-v1.00): Typo - Correction of the optionality (from ‘D’ to ‘O’) of the Data Item <CONSIGNMENT-HOUSE CONSIGNMENT-CONSIGNMENT ITEM-ADDITIONAL REFERENCE.Reference Number> in messages CC017C, CD018C and CC044C [because no Condition is applied]. Alignment to the DDNTA-6.2.0-v1.00 (NCTS-P6), formally accepted by ECCG written procedure. | Yes | Documentary | ! SFA to NPM AFTER CAB Typo Q2 No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 20 | RFC_NCTS_0209_IAR-UCCNCTS2881_v1.00(SfA-NPM).docx | RFC_NCTS_0209 | Documentary | - - APPROVED by NPMs - - Cleaning of XSD. Nice to have. Consistent with RFC_AES_0143. | NCTS-P5 (DDNTA-5.15.0-v1.00 – Appendix X: Correction of ‘stypes.xsd’ & ‘ctypes.xsd’ by removing the unused simple types "NumType"; removal tag "xsdBaseType" in complex type; correction of simple data type "NumType" (xs:token -> xs:integer). Alignment to the DDNTA-6.2.0-v1.00 (NCTS-P6), formally accepted by ECCG written procedure. | Yes | Both | ! SFA to NPM AFTER CAB Alignment with NCTS-P6 DDNTA validated by ECCG No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 21 | RFC_NCTS_0210_IAR-UCCNCTS2857-v1.00(SfA-NPM).docx | RFC_NCTS_0210 | Documentary | - - APPROVED by NPMs - - G0017 improved to clarify when the data item 'State of seals' in CD018C (and CC044C) includes the value ‘0’ or ‘1’. | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-51.8.0): Amendment of G0017 to clarify the state of seals reported. Alignment to the DDNTA-6.2.0-v1.00 (NCTS-P6), formally accepted by ECCG written procedure. | Yes | Both | ! SFA to NPM AFTER CAB Alignment with NCTS-P6 DDNTA validated by ECCG No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 22 | RFC_NCTS_0211_IAR-UCCNCTS2259-v1.10(SfA2-NPM).docx | RFC_NCTS_0211 | Documentary | - - APPROVED by NPMs - - G0190 added to clarify the meaning of 'requesting' and 'requested' offices in IE150 and IE151. | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-51.8.0): Adding G0190 to clarify in CD150C and CD151C the usage of ‘CUSTOMS OFFICE OF RECOVERY REQUESTING’ and ‘CUSTOMS OFFICE OF RECOVERY REQUESTED’. Alignment to the DDNTA-6.2.0-v1.00 (NCTS-P6), formally accepted by ECCG written procedure. | yes | CD only | ! SFA to NPM AFTER CAB Alignment with NCTS-P6 DDNTA validated by ECCG (as per NA-AT) No change compared to NCTS_Emergency-RFC-List.37-v04(SfA-NPM+IMPL) 2023-01-31.7z
RFC-List.37 | 23 | RFC_NCTS_0212_IAR-UCCNCTS2961-v1.10(SfA-NPM+NPM).docx | RFC_NCTS_0212 | As soon as possible, before 01.12.2023 (but recommended before entering in NCTS-P5 operations in Common Domain) | - - APPROVED by NPMs - - Outcome of the discussion in PICS FORUM. Avoiding confusion in case of goods packaged together. Managing the Transitional Period. Consistent with RFC_AES_0136. | NCTS-P5 (DDNTA-5.15.0-v1.0.0 - CSE-v51.8.0): Description of rule R0364 shall be corrected and new rules and transition rules added, to properly manage the situation of goods packed together, during and after the Transitional Period. | Yes | Both | ! SFR to NPM AFTER CAB Resolving the PICS FORUM discussions EXTRA IMPLEMENTATION DETAILS INCLUDED IN SUPPORTING DOCUMENT OF DDNTA-5.15.1-v1.00-SfA RFC_NCTS_0212_IAR-UCCNCTS2961-v1.00(SfA-NPM).docx replaced by RFC_NCTS_0212_IAR-UCCNCTS2961-v1.10(SfA-NPM+IMPL).docx
RFC-List.xx | 24 | RFC_NCTS_0213_IAR-UCCNCTS2677-v0.30(SfR-NPM).docx | RFC_NCTS_0213 | STOPPED - No implementation | - - REJECTED - - Major objections from ES, DE, NL. | NCTS-P5 (DDNTA-5.15.0-v1.00 CSE-v51.8.0) D.G. <TRANSPORT DOCUMENT>: shall be kept at Consignment Item level after the Transitional Period; other corrections for this D.G.. | - | - | Rejected
25
RFC-List.37 | 26 | RFC_NCTS_0214_IAR-UCCNCTS3420-v1.00(SfA-Applied by NAs in PROD).docx | RFC_NCTS_0214 | As early as possible | - - APPROVED by NPMs of NAs in operations - - 1. Impact on ED if not aplied: CC015C would be rejected in case of P5 declarations type 'T' with a mix of T1 and T2F [No Office of Transit required]. 2. Risk if this proposal is not applied: messages from DE-ES-SI will be rejected by the P5 country not aligned. 2. Risk if this proposal is applied: the valid P5 messages from DE-ES-SI might be rejected by the P4 country based on C030. Mitigation: C030 is likely not applied, else there would be many P4 rejections observed on the CD via CS/MIS2. Most impact for the countries having many movement from/to territories with special fiscal status. Ideally before starting P5 operations, but not mandatory, depending on business context. | NCTS-P5 (DDNTA-5.15.0-v1.0.0 - CSE-v51.8.0): Correction of B1836 – No Office of Transit required to move EU goods with T2F (Fiscal territories). Fixing the B1836 [that disables the C0030 during TP] to avoid rejection when moving EU Goods to Fiscal Territories in case of a mix of T1 and T2F declaration types (both Technical and Functional Descriptions shall be fixed). | Yes | Both | Applied in DDNTA-5.15.1-v1.00, to eliminate rejections observed between NTA.DE and NTA.ES in February 2023. Applied in DROOLS (TRP-5.12.3 and CRP-5.7.7.1). Also applied by NA-DE, NA-ES and NA-SI in Production in February 2023.
RFC-List.37 | 27 | RFC_NCTS_0215_IAR-UCCNCTS3399+3404-v1.00(SfA-applied by NAs in PROD and CTS).docx | RFC_NCTS_0215 | Step_1: was applied in ieCA. Step_2: as early as possible | - - APPROVED by NPMs of NAs in operations - - Implementation in two steps, to offer flexibility to NAs. The ieCA already apply a workaround. | NCTS-P5 (DDNTA-5.15.0-v1.00 - CSE-v51.8.0): Correction of B1896 and CTS for downgrading a transit declaration with EXS, without UCR & without Transport Document [keeping C547 not violated]. Avoiding the rejection of CD001B (and similar Common Domain messages) due to C547, with a CTS change for downgrade, along with a slight change in the P5 External Domain (i.e. change on the B1896 [that aims to be equivalent to C547 during TP]) and without changing the Legacy applications. | Yes | Both | Applied in DDNTA-5.15.1-v1.00, to eliminate rejections observed between NTA.SI and NCTS-P4 countries in February 2023. Applied in DROOLS (TRP-5.12.4 and CRP-5.7.7.2). Also applied by NA-DE, NA-ES and NA-SI in Production in February 2023.
RFC-List.37 | 28 | RFC_NCTS_0216_CSRD2-CL754-v1.00(SfA-NPM).docx | RFC_NCTS_0216 | Implemented via CS/RD2 | - - APPROVED by NPMs of NAs in operations - - Correction of the content of codelist CL754 for transport document type (TIR carnet number). | CS/RD2 DATA: correction of CL754 (TransportDocumentType) for NCTS-P5 only (CONF & PROD) and correction of CL999 (DomainMapping) The entry N952 (TIR Carnet) is not needed in CL754 (TransportDocumentType) because the TIR Carnet information should not be included in the Data Group ‘TRANSPORT DOCUMENT’ to avoid duplicate info and to avoid more than one TIR Carnet per Transit declaration. Logically, this correction also impacts the CL999 (for the future). Change applied on 02.03.2023 in CS/RD2 CONF and CS/RD2 PROD with validity date 07.03.2023. | Yes | Both (via codelist) | Applied in CS/RD2 / NCTS-P5, to eliminate rejections observed between NTA.SI and NCTS-P4 countries in February 2023. Applied in CS/RD2 PROD (and automatically loaded in CRP).
RFC-List.38 | 29 | RFC_NCTS_0218_IAR-UCCNCTS-3366(SfA2-NPM)-v3.01a = Approved ECCG.docx | RFC_NCTS_0218 | TAXUD: Implemented in CS/RD2 and in NCTS-CRP(ieCA) NA: 01.12.2023 | - - APPROVED by ECCG on 05.10.2023 - - To translate in technical terms the content of the UCC Work Programme update and IRTA update that will be adopted before 01.12.2023. | TPendDate is changed from 01.12.2023 to 21.12.2025. The deadline of 01.12.2023 remains, but for the CORE functionalities only. | Yes | Both | Applied in DDNTA-5.15.2-v2.00(SfA-NPM). Applied in CS/RD2 CONF and CS/RD2 PROD (validity date 12.10.2023) Applied in NCTS-CRP-5.8.4 (loaded in ieCA PROD & ieCA CONF)
RFC-List.39 | 30 | RFC_NCTS_0219_IAR-UCCNCTS-3221-v1.09.docx | RFC_NCTS_0219 | NA: TPendDate (21.01.2025) | Alignment to Legal Basis (Country of dispatch) | Correction to get DDNTA aligned with the Convention on a Common transit procedure (Annex A1a), the Data Item “Country of dispatch” becomes required after the TPendDate. In addition, it should not only be limited to the TIR movements, therefore the Data Item is added in all relevant messages (ED & CD). | Yes | Both | Applied in DDNTA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | 31 | RFC_NCTS_0220_IAR-UCCNCTS-3912-v1.06.docx | RFC_NCTS_0220 | NA: TPendDate (21.01.2025) | Alignment to Legal Basis (Country of destination) | Correction to get DDNTA aligned with the Convention on a Common transit procedure (Annex A1a), the Data Item “Country of destination” remains required. But it should not only be possible at MC or HCI levels, but also at the House Consignment level. The Data Item is added as HC level, in all relevant messages (ED & CD). | Yes | Both | Applied in DDNTA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | 32 | RFC_NCTS_0221_IAR-UCCNCTS-3481-v1.07.docx | RFC_NCTS_0221 | NA: TPendDate (21.01.2025) | Correction of C0587 for the Post Transition Period (only) | The condition applied on the data group 'Office of Exit for Transit' can be corrected and will be changed in a synchronised way, taking advantage of the BRT mechanism. | Yes | Both | Applied in DDNTA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | 33 | RFC_NCTS_0222_IAR-UCCNCTS-3765-v1.05.docx | RFC_NCTS_0222 | NA: TPendDate (21.01.2025) | Correction of C0001 for the Post Transition Period (only) - Taking into account the RFC_NCTS_0220. | The condition C0001 is applied on Data Element 'Consignee'. During Transitional Period, the C0001 is deactivated by a BRT. The C0001 needs to be fixed, and fully aligned to the legal basis. | Yes | Both | Applied in DDNTA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | 34 | RFC_NCTS_0223_IAR-UCCNCTS-3442-v1.02.docx | RFC_NCTS_0223 | NA: TPendDate (21.01.2025) | HC 99x --> 1999x: as recommended by ECCG and TCG. | Increasing the maximum number of House consignments in one declaration (from 99x to 1999x). | Yes | Both | Applied in DDNTA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | 35 | RFC_NCTS_0224_IAR-UCCNCTS-4308-v1.00.docx | RFC_NCTS_0224 | NA: TPendDate (21.01.2025) | Possibility to have in IE018 (and IE044) the gross mass = '0' (zero) at HC level. [like at MC and HCI levels]. | Adding the G0021 and correcting the Appendix X (stypes.xsd) to use <xsdBaseType value=”DecimalWithZero_16_6” />. | Yes | Both | Applied in DDNTA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | 36 | RFC_AES-P1_0152_NCTS-P5_0225_NCTS-P6_0034_IAR-UCCAES2298-UCCNCTS3770-UCCNCTSP6-66-v1.00.docx | RFC_NCTS_0225 | Documentary change applied | No impact on NA. | History of Rules and Conditions moved from DMP file to DDNTA Appendix D. | - | No impact | Applied in DDNTA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | 37 | RFC_DDCOM_0030_SOFTDEV-IAR-UCCNCTS-4024(SfA)-v2.00.docx | RFC_DDCOM_0030 | Assumed to be a documentary change for all. | To avoid rejections on the Common Domain, it must be clarified that - NAs should follow specific CSI conventions when exchanging messages with ieCA, as specified in ieCA SAD v3.60, - the CSI MsgID is recommended to be unique for clear identification of each message. | Improvement on CSI MsgID and CSI message conventions related to ieCA. | - | CD related - No impact expected | Applied in DDCOM-20.4.1-v2.00(SfA-NPM).
RFC-List.39 | 38 | RFC_DDCOM_0031_SOFTDEV-IAR-UCCNCTS-3445(SfA)-v2.00.docx | RFC_DDCOM_0031 | Assumed to be a documentary change for all. | To avoid rejections on the Common Domain, it must be clarified that the Data Items "Message identification" and "Correlation identifier" must be handled in case sensitive mode. | Clarification in "VII.7.4 Message identification" and "VII.7.5 Correlation identifier" that those Data Elements are case sensitive. | - | CD related - No impact expected | Applied in DDCOM-20.4.1-v2.00(SfA-NPM).
RFC-List.39 | 39 | RFC_DDCOM_0032_SOFTDEV-IAR-UCCNCTS-3560(SfA)-v1.00.docx | RFC_DDCOM_0032 | Assumed to be a documentary change for all. | Update section "IV.3.1.1 Rules/Conditions Validation Principles for External Domain IEs" in order to split the validation of R&C into strictly mandatory (stipulated by legislation) and those that their relaxation shall be avoided to secure the quality of data. | Improvement on semantic validation principles for External Domain messages. | - | ED & CD related - No impact expected | Applied in DDCOM-20.4.1-v2.00(SfA-NPM).
RFC-List.39 | 40 | RFC_DDCOM_0033_SOFTDEV-IAR-UCCNCTS-3561(SfA)-v2.01.docx | RFC_DDCOM_0033 | Assumed to be a documentary change for all. | To avoid rejections when pushing IE411 messages to CS/MIS2, it must be clarified - how the combined statistics for multiple domains should be sent (A), - that in one specific IE411, for one specific statistic type, only one value shall be included per period and per country pair (B). Considering the choices made when implementing CS/MIS2 (including the latest release v3.1.0.0), the references to IE412 in DDCOM document are obsolete and should be removed (C). | Update of section II.2.3 to clarify IE411 message and the submission of combined statistics for AES and NCTS-P5 and various updates of sections II, X and XI due to the removal of IE412. | - | CD related - No impact expected | Applied in DDCOM-20.4.1-v2.00(SfA-NPM).
RFC-List.39 | 41 | RFC_DDCOM_0034_SOFTDEV-IAR-UCCNCTS-4313(SfA)-v1.00.docx | RFC_DDCOM_0034 | Documentary change relevant for some countries. | Definition of the naming convention for the local CCN/CSI queue, which may be created by the countries interested to use them for splitting the flow of messages pushed to the Legacy and To-Be applications (in case of 2 DB architecture during the Transitional Period). | Insertion of the Table 69: Names of the optional Local Queues (if used for the purpose of transition). | - | ND related - No impact on CD nor ED | Applied in DDCOM-20.4.1-v2.00(SfA-NPM).

## RFC--List_AES+DDCOM
RFC-List | Filename (SfA) | ID | Deadline for implementation | Comment | In short | A1 | Impact CD/ED | Note
RFC-List.38 | RFC_AES_0149_SDEV-RFC-IAR-UCCAES2099(SfA2-NPM)-v3.01a = Approved ECCG.docx | RFC_AES_0149 | TAXUD: Implemented in CS/RD2 and in NCTS-CRP(ieCA) NA: 01.12.2023 | - - APPROVED by ECCG on 05.10.2023 - - To translate in technical terms the content of the UCC Work Programme update and IRTA update that will be adopted before 01.12.2023. | TPendDate is changed from 01.12.2023 to 11.02.2025. The deadline of 01.12.2023 remains, but for the CORE functionalities only. | Yes | Both | Applied in DDNXA-5.15.2-v2.00(SfA-NPM). Applied in CS/RD2 CONF and CS/RD2 PROD (validity date 12.10.2023) Applied in AES-CRP-5.8.6 (loaded in ieCA PROD & ieCA CONF)
RFC-List.39 | RFC_AES_0145_SDEV-RFC-IAR-UCCAES2002-v1.01-(SfR-NPM).docx | RFC_AES_0145 | Different proposal for ED and CD latest @ TPendDate (11.02.2025) | Replacement of CL294 with CL194 for some ED and CD Ies - simplification requested by differnet NAs | CL194 to replace CL294 in some ED and CD IEs in order to declare EIN Customs Offices of Exit in export followed by transit (EFBT) cases | Yes | Both | Applied in DDNXA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | RFC_AES_0146_SDEV-RFC-IAR-UCCAES2034-v1.01-(SfR-NPM).docx | RFC_AES_0146 | NA: TPendDate (11.02.2025) | Correction of R0530 | Correction of R0530 needed as to align with the situation when the NCTS Recovery procedure is started, in the case of EFBT | No | CD related - Low impact expected | Applied in DDNXA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | RFC_AES_0148_SDEV-RFC-IAR-UCCAES2098-v1.01-(SfR-NPM).docx | RFC_AES_0148 | NA: TPendDate (11.02.2025) | Recapitulative Supplementary declaration | Recapitulative supplementary declaration a new external domain message was created with some new codelists, conditions, guidelines and rules attached | No | Both | Applied in DDNXA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | RFC_AES_0151_SDEV-RFC-IAR-UCCAES2228-v1.01-(SfR-NPM).docx | RFC_AES_0151 | NA: TPendDate (11.02.2025) | Corrections in SI level, rolling changes back regarding transitional D.G.s for AES-P1 by removing the 'Transport Document' D.G. from SI level after TPendDate | Revert back the changes introduced by the RFC_AES_0135_SDEV-RFC-IAR-UCCAES1677-v1.10 (SfA-NPM+IMPL), part of RFC-List.37, and discontinue the usage of 'Transport Document' at Goods Shipment/Goods Item level after TP | Yes | Both | Applied in DDNXA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | RFC_AES_0153_SDEV-RFC-IAR-UCCAES2457-v1.01-(SfR-NPM).docx | RFC_AES_0153 | NA: TPendDate (11.02.2025) | Rule to restrict only one occurrence of 'C651'/’C658’ under PREVIOUS DOCUMENT.Type, per goods item | R0894 is introduced in order to restrict only one occurrence of PREVIOUS DOCUMENT.Type that is equal to 'C651'/’C658’ per goods item. | Yes | Both | Applied in DDNXA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | RFC_AES_0152_NCTS-P5_0225_NCTS-P6_0034_IAR-UCCAES2298-UCCNCTS3770-UCCNCTSP6-66-v1.00.docx | RFC_AES_0152 | Documentary change applied | No impact on NA. | History of Rules and Conditions moved from DMP file to DDNXA Appendix D. | - | No impact | Applied in DDNXA-5.15.2-v2.00(SfA-NPM).
RFC-List.39 | RFC_DDCOM_0030_SOFTDEV-IAR-UCCNCTS-4024(SfA)-v2.00.docx | RFC_DDCOM_0030 | Assumed to be a documentary change for all. | To avoid rejections on the Common Domain, it must be clarified that - NAs should follow specific CSI conventions when exchanging messages with ieCA, as specified in ieCA SAD v3.60, - the CSI MsgID is recommended to be unique for clear identification of each message. | Improvement on CSI MsgID and CSI message conventions related to ieCA. | - | CD related - No impact expected | Applied in DDCOM-29.4.1-v2.00(SfA-NPM).
RFC-List.39 | RFC_DDCOM_0031_SOFTDEV-IAR-UCCNCTS-3445(SfA)-v2.00.docx | RFC_DDCOM_0031 | Assumed to be a documentary change for all. | To avoid rejections on the Common Domain, it must be clarified that the Data Items "Message identification" and "Correlation identifier" must be handled in case sensitive mode. | Clarification in "VII.7.4 Message identification" and "VII.7.5 Correlation identifier" that those Data Elements are case sensitive. | - | CD related - No impact expected | Applied in DDCOM-29.4.1-v2.00(SfA-NPM).
RFC-List.39 | RFC_DDCOM_0032_SOFTDEV-IAR-UCCNCTS-3560(SfA)-v1.00.docx | RFC_DDCOM_0032 | Assumed to be a documentary change for all. | Update section "IV.3.1.1 Rules/Conditions Validation Principles for External Domain IEs" in order to split the validation of R&C into strictly mandatory (stipulated by legislation) and those that their relaxation shall be avoided to secure the quality of data. | Improvement on semantic validation principles for External Domain messages. | - | ED & CD related - No impact expected | Applied in DDCOM-29.4.1-v2.00(SfA-NPM).
RFC-List.39 | RFC_DDCOM_0033_SOFTDEV-IAR-UCCNCTS-3561(SfA)-v2.01.docx | RFC_DDCOM_0033 | Assumed to be a documentary change for all. | To avoid rejections when pushing IE411 messages to CS/MIS2, it must be clarified - how the combined statistics for multiple domains should be sent (A), - that in one specific IE411, for one specific statistic type, only one value shall be included per period and per country pair (B). Considering the choices made when implementing CS/MIS2 (including the latest release v3.1.0.0), the references to IE412 in DDCOM document are obsolete and should be removed (C). | Update of section II.2.3 to clarify IE411 message and the submission of combined statistics for AES and NCTS-P5 and various updates of sections II, X and XI due to the removal of IE412. | - | CD related - No impact expected | Applied in DDCOM-29.4.1-v2.00(SfA-NPM).
RFC-List.39 | RFC_DDCOM_0034_SOFTDEV-IAR-UCCNCTS-4313(SfA)-v1.00.docx | RFC_DDCOM_0034 | Documentary change relevant for some countries. | Definition of the naming convention for the local CCN/CSI queue, which may be created by the countries interested to use them for splitting the flow of messages pushed to the Legacy and To-Be applications (in case of 2 DB architecture during the Transitional Period). | Insertion of the Table 69: Names of the optional Local Queues (if used for the purpose of transition). | - | ND related - No impact on CD nor ED | Applied in DDCOM-20.4.1-v2.00(SfA-NPM).

## Info
Version | Date | Comment
v01.00 | 2023-01-10 | The list of 22 corrections with status "SfA-NPM"- To get blocking issues fixed and to get the typo removed. Also includes corrections aligned to AES, and the corrections already applied for NCTS-P6.
v01.10 | 2023-01-31 | Updated with "Implementation details". Also implements the comments received from Nas until 20.01.20223. Confirms that one SfR is accepted; one SfR is rejected.
v01.20 | 2023-03-10 | Updated with "Implementation details" for RFC_NCTS_0194, RFC_NCTS_0197, RFC_NCTS_0204 and RFC_NCTS_0212 Also includes 3 extra emergency corrections applied to resolve the issues identified during the first P5 exchanges on the Common Domain. All changes have been implemented in DDNTA-5.15.1-v1.00, in CTS-5.7.5 or CS/RD2 PROD.
v02.00 | 2023-10-12 | Extended with RFC-List.38 and RFC-List.39 All NCTS changes have been implemented in DDNTA-5.15.2-v1.00(SfR-NPM) and CS/RD2 PROD. All DDCOM changes have been implemented in DDCOM-20.4.1-v1.00(SfR-NPM).
v02.01 | 2023-10-17 | Extended with one sheet with information for AES (RFC-List.38 and RFC-List.39, incl. (same) DDCOM part).
v02.02 | 2023-12-07 | Update of the NCTS sheet to include the latest version of the DOCX files for the changes of RFC-List.39. Addition of RFC_NCTS_0224 and RFC_DDCOM_0034. All NCTS changes are alignd with the implementation done in DDNTA-5.15.2-v2.00(SfA-NPM) and CS/RD2 PROD. All DDCOM changes are alignd with the implementation done in DDCOM-20.4.1-v2.00(SfA-NPM).
Published on CIRCABC on 07-12-2023
https://circabc.europa.eu/ui/group/74357351-7c61-4729-8f4b-cd92c213ba34/library/c65edaf5-bf3b-4fb2-8fdc-ca13f7b8375b?p=1&n=-1&sort=modified_DESC
File details of RFC-Proposals
RFC-List.38 (DDNTA)
RFC-List.39 (DDNTA)
RFC-List.39 (DDCOM)
RFC-List.39 (DDNXA)